## Sheet1
SI | Module | UAT Points | Remarks/Comments | Status | ETA
1 | Arcchitect | OBPAS Dashboard needs to be redesign for Architect User 1. Design Shared 2. Design Approved 3. Designed Pending | Need further discussion | Pending
2 |  | Output of "Shared Scrutiny Plan" will come to Architect's Dashboard |  | Pending | 2024-07-04
3 |  | "Plan Shared with Lessee" instead of "Shared Scrutiny Plan" and Shared Scrutiny Plan will merge in Dashboard only |  | done
4 |  | One icon to be incorporated in scrutiny tool |  | Pending
5 |  | Service Type will be changed as below, >> New Construction >> Addition/Alternation >> Revision >> Plot Development/ Hill Cutting | In case of Plot Development/ Hill Cutting - Lessee will apply from the portal for TC and this will directly go to MS for approval | Pending | 2024-07-05
6 |  | Questionnaire to be updated in scrutiny report only Questionnaire upload button will be removed |  | Pending | 2024-07-05
7 |  | Certificate from Architecture/Engineer' will 'Certificate from Architect/Engineer...' |  | done
8 |  | Lessee Share name should change to Additional Details |  | done
9 |  | After Plan share success popup should come and toast modal should not come |  | done
10 | Technical Clearance | Table format to updated in TC application (while selecting DCR) |  | done
11 |  | Remove affidavit & Power of Attorney buttons |  | Pending | 2024-07-05
12 |  | Two popups are coming after submission of TC application |  | done
13 |  | Redesign the Digital Signature button/functionality |  | Pending
14 |  | In GME login Construction License Fee should show, Similarly MS login only TC fee should show |  | done
15 |  | Payment done section should be removed from Employee's login under Payment Details |  | done
16 |  | Search by Application No' to be changed to 'Search by DCR no' |  | done
17 |  | Lessee details should be removed from menu as Lessee only applying for TC |  | done
18 |  | "Save & Next" button will be only "Next" button |  | done
19 |  | Digitally Signed (in Self Declaration screen)template pending from Lessee's login And this page should have Save&Next button |  | Pending | 2024-07-04
20 |  | Under Payment Details tab, amounts should show comma separated and Total Payable should show correctly |  | done
21 |  | One error page is coming, after payment success popup |  | done
22 |  | Payment date should show current system date |  | done
23 |  | Under Payment Details tab, notes should not show |  | done
24 |  | After Application submission, message should "Application Submitted Successfully" instead of Application Created Successfully. |  | done
25 |  | After TC & CL, notification should go to all Engineering Section like FM (Site), FM(HQ) Area Manager, DGM (E), GM(E) including MD |  | done
26 | Occupancy Certificate | For Part Occupancy, error message should show "For Part Occupancy minimum 30% is required" |  | Pending | 2024-07-04
27 |  | Noting is not required for FM (Site) for schedule appointment |  | Pending | 2024-07-04
28 |  | Action button should be center aligned in Schedule Inspection |  | Pending | 2024-07-04
29 |  | After OC application, the status should show "Under Field Inspection" |  | Pending | 2024-07-04
30 |  | We need to redesign entire 'Field Inspection' Window |  | Pending | 2024-07-04
31 |  | Remove Obtained Occupancy |  | Pending | 2024-07-04
32 |  | Remove NOC details from FM (Site) login |  | Pending | 2024-07-04
33 |  | New design required for Field Inspection & Schedule Inspection screens - Nitish |  | Pending | 2024-07-04
Date: 26-Jun-2024 |  |  |  | Status | ETA
1 |  | Instead of Architect it should be Architect/Engineer in Login page |  | done
2 |  | Architect Dashboard to be redesigned, and populate details as how many drawing shared, how many drawing have scrutinized etc. |  | Pending
3 |  | Increase Drawing upload size to 30MB |  | Pending
4 |  | Automatic PDF conversion of drawing is required, this should auto populate when Architect shares the drawing with Lessee |  | Pending
5 |  | We may need to integrate any viewer through which user can view .dxf files, so that comparison will be easier at Goa-IDC office end |  | Pending
6 |  | Separate invoice and separate fee structure to be incorporated in Technical Clearance Payment Details | We can discuss more with MD sir regarding this
7 |  | At present system, download TC order and CL order is not working |  | done
8 | Technical Clearance | FM (Site) role to be incorporated in Technical Clearance Application workflow, the workflow would be as below, Lessee -> FM (Site) -> MS (Approver) |  | done
9 | Completion Order | One additional upload option is required under Lessee's login in Completion Order Application with below naming convention, Other Document [Scanned copy of previous approved Construction Licenses (if Applicable)] |  | Pending | 2024-07-04
10 | Filed Inspection Report | After FM (site) Schedule's appointment with lessee, a notification will go to Architect as well. So that Lessee can bring Architect for Physical Inspection. Same should be applicable for Technical Clearance as well (a notification should go to Architect when Lessee applies for TC from the portal) |  | Pending | 2024-07-04
11 |  | In FM's Report, Occupancy Achieved (i) <- questions will come when FM hovers on (i) icon For all questions this should be followed across |  | Pending | 2024-07-04
12 |  | Any other remarks will become below, Any other remarks (including special condition) |  | Pending | 2024-07-04
13 |  | Approved Plan Number will be Construction License number and the should be auto populate and along with date |  | Pending | 2024-07-04